## Sheet1
ID | Story ID | Story Name | Short Description/ Task | Story # and details | Sprint Cycle Number | Resources working | Hardware or Software | Progress
1 | 1 | 4-Year Plan of Study | Obtain database | Story 1 Paragraph 4 | 3 | Yaby | Software | In progress
19 | 7 | GSU Student Planner Website | Create website | Story 7 Paragraph 3 | 1 | Nick | Software | Complete
20 | 7 | GSU Student Planner Website | Create a registration form | Story 7 Paragraph 3 | 3 | Nick | Software | In progress
2 | 1 | 4-Year Plan of Study | Create a layout | Story 1 Paragraph 5 | 3 | Yaby | Software | In Progress
3 | 1 | 4-Year Plan of Study | Organize classes on layout | Story 1 Paragraph 5 | 3 | Yaby | Software | In Progress
21 | 7 | GSU Student Planner Website | Create a login page | Story 7 Paragraph 3 | 3 | Caleb | Software | In progress
22 | 7 | GSU Student Planner Website | Create a profile page | Story 7 Paragraph 3 | 3 | Nick | Software | In progress
23 | 7 | GSU Student Planner Website | Create tabs for each resource | Story 7 Paragraph 4 | 2 | Nick | Software | Complete
4 | 2 | Scheduled Route | Obtain the specific users class schedule. | Story 2 Paragraph 1 | 3 | Nick | Software | In Progress
5 | 2 | Scheduled Route | Create a route | Story 2 Paragraph 2 | 3 | Nick | Software | In Progress
6 | 2 | Scheduled Route | Add any additional destinations and save changes | Story 2 Paragraph 3 | 3 | Nick | Software | In Progress
7 | 3 | Change Class Schedule | Reset account password | Story 3 Paragraph 2 | 3 | Caleb | Software | In Progress
8 | 3 | Change Class Schedule | Change class schedule | Story 3 Paragraph 4 | 4 | Caleb | Software | Not Started
9 | 3 | Change Class Schedule | Class change reflected on scheduled route | Story 3 Paragraph 5 | 4 | Caleb | Software | Not Started
10 | 4 | Degree Works Implementation | Degree Works login in pop up window | Story 4 Paragraph 4 | 4 | Iori | Software | Not Started
11 | 4 | Degree Works Implementation | Have Degree Works operaring within our site | Story 4 Paragraph 5 | 4 | Iori | Software | Not Started
12 | 4 | Rate My Professor Implementation | Have Rate My Professor operaring within our site | Story 4 Paragraph 5,6 | 5 | Iori | Software | Not Started
13 | 5 | Grades | Create a grades window which would populate with classes based on the 4 year plan | Story 5 Paragraph 3 | 5 | Mohit | Software | Not Started
14 | 5 | Grades | Make data editable by student | Story 5 Paragraph 3 | 5 | Mohit | Software | Not Started
15 | 5 | Grades | Create a grade calculator to calculate future goals. | Story 5 Paragraph 4 | 3 | Mohit | Software | Not Started
16 | 6 | Electives | Obtain the database information about the electives offered for a degree | Story 6 Paragraph 3 | 5 | Stuti | Software | Not Started
17 | 6 | Electives | Create a table that shows the class with a brief description | Story 6 Paragraph 3 | 5 | Stuti | Software | Not Started
18 | 6 | Electives | Populate the table with the semesters the course is offered in | Story 6 Paragraph 3 | 5 | Stuti | Software | Not Started